## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Milestone 1 | Milestone 1 | US-M1-ENV | Set up Java, IntelliJ IDEA, MySQL, Git, Postman and create/run the Spring Boot project. | Must Have | Development environment | Kishore Kumar | Completed
Milestone 1 | Milestone 1 | US-M1-DB | Design the database with Users, Beneficiary, Scheme, Application, Verification, Approval, Disbursement and Audit Log tables and relationships. | Must Have | Project requirements | Ravi Teja | Completed
Milestone 1 | Milestone 1 | US-M1-API | Design the complete REST API list and system workflow for registration, login, schemes, applications, eligibility, verification, approval, disbursement and reports. | Must Have | Project requirements | Akshara | Completed
Milestone 1 | Milestone 1 | US-M1-WF | Design application, eligibility, verification, approval and disbursement workflows and research the required business logic. | Must Have | Project requirements | SreeLakshmi | Completed
Milestone 2 | Milestone 2 | US-M2-BEN | Develop Beneficiary CRUD APIs and connect the beneficiary module with the database. | Must Have | Database | Kishore Kumar | Completed
Milestone 2 | Milestone 2 | US-M2-SCH | Develop Scheme CRUD APIs, sample schemes and scheme retrieval functionality. | Must Have | Database | Kishore Kumar | Completed
Milestone 2 | Milestone 2 | US-M2-AUTH | Implement login and role-based authentication for Admin, Field Officer, District Officer and Finance Officer. | Must Have | User/role design | Niharika | Completed
Milestone 2 | Milestone 2 | US-M2-APP | Implement Application Submission backend module with validation and REST APIs. | Must Have | Beneficiary + Scheme | Akshara | Completed
Milestone 2 | Milestone 2 | US-M2-ELIG | Implement eligibility scoring logic and store eligibility results in the database. | Must Have | Application + Database | Ravi Teja | Completed
Milestone 2 | Milestone 2 | US-M2-WORK | Implement field verification, district verification, finance approval, routing and status update workflow. | Must Have | Application + Eligibility | SreeLakshmi | Completed
Milestone 3 | Milestone 3 | US-M3-DISB | Build milestone-wise disbursement scheduling, disbursement plan and compliance milestone functionality. | Must Have | Application + Workflow | Niharika / Kishore Kumar / Ravi Teja | Completed
Milestone 3 | Milestone 3 | US-M3-ANL | Build scheme-wise, region-wise, budget exhaustion and beneficiary category-wise analytics APIs. | Must Have | Scheme + Application + Disbursement | Akshara | Completed
Milestone 3 | Milestone 3 | US-M3-DASH | Build and integrate the analytics dashboard with live APIs and category-wise distribution views. | Must Have | Analytics APIs | SreeLakshmi | Completed
Milestone 3 | Milestone 3 | US-M3-EXPORT | Build PDF and Excel exports for disbursement and pending/non-compliance reports. | Must Have | Analytics + Disbursement | Akshara | Completed
Milestone 4 | Milestone 4 | US-M4-SEC | Implement JWT authentication, BCrypt password hashing, RBAC and method-level authorization across protected APIs. | Must Have | All backend modules | Niharika | Completed
Milestone 4 | Milestone 4 | US-M4-API | Secure existing REST APIs and implement treasury and beneficiary integration endpoints with error handling and API documentation. | Must Have | RBAC | Kishore Kumar | Completed
Milestone 4 | Milestone 4 | US-M4-AUD | Implement audit logging for verification, approval, disbursement and milestone actions and provide restricted audit-log retrieval. | Must Have | Workflow + Security | Ravi Teja | Completed
Milestone 4 | Milestone 4 | US-M4-FE | Implement frontend login, protected routes, role-based route guards, sidebar visibility and logout/token handling. | Must Have | Authentication API | SreeLakshmi | Completed
Milestone 4 | Milestone 4 | US-M4-QA | Prepare deployment configuration, final documentation, end-to-end QA, testing evidence and final project report. | Must Have | All modules | Akshara | Completed

## Sprint Backlog
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
US-M1-ENV | M1-K1 | Set up Java, IntelliJ IDEA, MySQL, Git and Postman and create the Spring Boot project. |  |  | Kishore Kumar | Environment Setup | Completed | 6 | Day 1: 6
US-M1-DB | M1-R1 | Identify required database tables, columns, primary keys, foreign keys and relationships. |  |  | Ravi Teja | Database Design | Completed | 5 | Day 1: 5
US-M1-DB | M1-R2 | Prepare ER diagram and database design document. |  |  | Ravi Teja | ER Design | Completed | 5 | Day 2: 5
US-M1-API | M1-A1 | Define REST API standards, base URL, HTTP methods, JSON format and authentication approach. |  |  | Akshara | API Design | Completed | 4 | Day 1: 4
US-M1-API | M1-A2 | Prepare REST API list for registration, login, scheme, application, verification, approval, disbursement and reports. |  |  | Akshara | API Documentation | Completed | 6 | Day 2: 6
US-M1-WF | M1-S1 | Design end-to-end application flow from registration to fund release. |  |  | SreeLakshmi | Workflow Design | Completed | 5 | Day 1: 5
US-M1-WF | M1-S2 | Prepare eligibility, verification and approval workflow diagrams and business-logic notes. |  |  | SreeLakshmi | Business Logic | Completed | 6 | Day 2: 6
US-M2-BEN | M2-K1 | Create Beneficiary entity and CRUD repository/service/controller APIs. |  |  | Kishore Kumar | Beneficiary API | Completed | 8 | Day 1: 8
US-M2-SCH | M2-K2 | Create Scheme entity and CRUD repository/service/controller APIs with sample scheme data. |  |  | Kishore Kumar | Scheme API | Completed | 8 | Day 2: 8
US-M2-AUTH | M2-N1 | Implement login and role-based authentication for Admin, Field Officer, District Officer and Finance Officer. |  |  | Niharika | Authentication | Completed | 8 | Day 3: 8
US-M2-APP | M2-A1 | Create Application entity and database mapping. |  |  | Akshara | Application Backend | Completed | 5 | Day 3: 5
US-M2-APP | M2-A2 | Create ApplicationRepository using Spring Data JPA. |  |  | Akshara | Repository | Completed | 4 | Day 4: 4
US-M2-APP | M2-A3 | Create ApplicationService and service implementation for submission, retrieval, update and deletion. |  |  | Akshara | Service Layer | Completed | 6 | Day 5: 6
US-M2-APP | M2-A4 | Create ApplicationController endpoints and test Application REST APIs. |  |  | Akshara | REST API Testing | Completed | 6 | Day 6: 6
US-M2-ELIG | M2-R3 | Implement eligibility scoring logic and persist eligibility records. |  |  | Ravi Teja | Eligibility Engine | Completed | 8 | Day 4: 8
US-M2-WORK | M2-S3 | Implement verification routing for Field Officer, District Officer and Finance Officer. |  |  | SreeLakshmi | Workflow Engine | Completed | 8 | Day 4: 8
US-M2-TEST | M2-N2 | Integrate modules, resolve conflicts and perform end-to-end testing. |  |  | Niharika | Integration Testing | Completed | 8 | Day 6: 8
US-M3-MOD | M3-N1 | Design DisbursementPlan and ComplianceMilestone entity schema and push to repository. |  |  | Niharika | Core Build | Completed | 6 | Day 1: 6
US-M3-MOD | M3-K1 | Set up controller/service skeleton for Disbursement APIs. |  |  | Kishore Kumar | API Development | Completed | 6 | Day 1: 6
US-M3-MOD | M3-R1 | Study Milestone 2 code and create ComplianceMilestone entity and repository. |  |  | Ravi Teja | Compliance Module | Completed | 6 | Day 1: 6
US-M3-MOD | M3-S1 | Pick chart library and wireframe dashboard layout with mock data. |  |  | SreeLakshmi | Dashboard UI | Completed | 5 | Day 1: 5
US-M3-MOD | M3-A1 | Design analytics query layer for scheme-wise and region-wise fund utilization. |  |  | Akshara | Analytics API | Completed | 6 | Day 1: 6
US-M3-MOD | M3-N2 | Build core milestone-wise disbursement scheduling algorithm. |  |  | Niharika | Disbursement Logic | Completed | 8 | Day 2: 8
US-M3-MOD | M3-K2 | Build DisbursementPlanController create/view APIs. |  |  | Kishore Kumar | Disbursement API | Completed | 6 | Day 2: 6
US-M3-MOD | M3-R2 | Implement due-date calculation in ComplianceMilestone service. |  |  | Ravi Teja | Compliance Logic | Completed | 6 | Day 2: 6
US-M3-MOD | M3-S2 | Build dashboard components with mock data. |  |  | SreeLakshmi | Dashboard UI | Completed | 5 | Day 2: 5
US-M3-MOD | M3-A2 | Build AnalyticsController exposing scheme-wise and region-wise summary endpoints. |  |  | Akshara | Analytics API | Completed | 7 | Day 2: 7
US-M3-MOD | M3-N3 | Link milestone completion to fund release trigger. |  |  | Niharika | Business Logic | Completed | 6 | Day 3: 6
US-M3-MOD | M3-K3 | Build actual-vs-scheduled disbursement tracking API. |  |  | Kishore Kumar | Tracking API | Completed | 7 | Day 3: 7
US-M3-MOD | M3-R3 | Implement non-compliance auto-flagging logic. |  |  | Ravi Teja | Compliance Logic | Completed | 6 | Day 3: 6
US-M3-MOD | M3-S3 | Connect dashboard to analytics APIs so scheme/region charts use live data. |  |  | SreeLakshmi | Frontend Integration | Completed | 6 | Day 3: 6
US-M3-MOD | M3-A3 | Add budget exhaustion calculation and beneficiary category-wise distribution API. |  |  | Akshara | Analytics API | Completed | 7 | Day 3: 7
US-M3-MOD | M3-N4 | Run integration test for Finance Approval → Disbursement Plan → Milestone Tracking → Fund Release. |  |  | Niharika | Integration Testing | Completed | 7 | Day 4: 7
US-M3-MOD | M3-K4 | Finish disbursement schedule generation API and Postman-test Module 3 endpoints. |  |  | Kishore Kumar | API Testing | Completed | 7 | Day 4: 7
US-M3-MOD | M3-R4 | Add reminder automation for upcoming/overdue milestones. |  |  | Ravi Teja | Reminder Automation | Completed | 6 | Day 4: 6
US-M3-MOD | M3-S4 | Add budget exhaustion and approval turnaround-time charts using analytics APIs. |  |  | SreeLakshmi | Dashboard Analytics | Completed | 6 | Day 4: 6
US-M3-MOD | M3-A4 | Build PDF disbursement report export and start Excel export for pending milestones. |  |  | Akshara | Report Export | Completed | 7 | Day 4: 7
US-M3-MOD | M3-K5 | Fix API bugs found during frontend integration. |  |  | Kishore Kumar | Bug Fixing | Completed | 5 | Day 5: 5
US-M3-MOD | M3-R5 | Test compliance milestone flow end-to-end and fix bugs. |  |  | Ravi Teja | QA | Completed | 6 | Day 5: 6
US-M3-MOD | M3-S5 | Add category-wise distribution view and polish dashboard UI/UX. |  |  | SreeLakshmi | Dashboard Polish | Completed | 6 | Day 5: 6
US-M3-MOD | M3-A5 | Finish Excel export for non-compliance analysis and draft Milestone 3 documentation. |  |  | Akshara | Documentation | Completed | 6 | Day 5: 6
US-M3-MOD | M3-N5 | Review all PRs, resolve conflicts and re-test integration. |  |  | Niharika | Code Review | Completed | 6 | Day 5: 6
US-M3-MOD | M3-N6 | Perform final full-system test and prepare demo flow/team status summary. |  |  | Niharika | Demo Preparation | Completed | 6 | Day 6: 6
US-M3-MOD | M3-K6 | Prepare API documentation/collection for the demo. |  |  | Kishore Kumar | API Documentation | Completed | 5 | Day 6: 5
US-M3-MOD | M3-R6 | Prepare walkthrough of compliance milestone module. |  |  | Ravi Teja | Demo Preparation | Completed | 5 | Day 6: 5
US-M3-MOD | M3-S6 | Final dashboard polish and prepare demo screenshots/flow. |  |  | SreeLakshmi | Demo Preparation | Completed | 5 | Day 6: 5
US-M3-MOD | M3-A6 | Finalize Milestone 3 documentation and verify all exports work with real data. |  |  | Akshara | Documentation & QA | Completed | 6 | Day 6: 6
US-M4-SEC | N1 | Reviewed and finalized security architecture and role hierarchy for FIELD_OFFICER, DISTRICT_OFFICER, FINANCE_APPROVER and ADMIN. | 23-07-2026 | 23-07-2026 | Niharika | Security Architecture | Completed | 4 | Day 1: 4
US-M4-SEC | N2 | Defined and documented permissions for the four project roles. | 24-07-2026 | 24-07-2026 | Niharika | RBAC | Completed | 5 | Day 2: 5
US-M4-SEC | N3 | Reviewed authentication flow and identified protected/public backend endpoints. | 27-07-2026 | 27-07-2026 | Niharika | Authentication | Completed | 5 | Day 3: 5
US-M4-SEC | N4 | Prepared backend security configuration for authentication and authorization. | 28-07-2026 | 28-07-2026 | Niharika | Security Configuration | Completed | 5 | Day 4: 5
US-M4-SEC | N5 | Reviewed BCrypt password-hashing and user authentication requirements. | 29-07-2026 | 29-07-2026 | Niharika | Authentication | Completed | 4 | Day 5: 4
US-M4-SEC | N6 | Applied and reviewed role-based restrictions for backend endpoints. | 30-07-2026 | 30-07-2026 | Niharika | RBAC | Completed | 6 | Day 6: 6
US-M4-SEC | N7 | Reviewed backend changes from team members for security and role consistency. | 31-07-2026 | 31-07-2026 | Niharika | Integration Oversight | Completed | 4 | Day 7: 4
US-M4-SEC | N8 | Tested authentication and authorization scenarios for all defined roles. | 03-08-2026 | 03-08-2026 | Niharika | Security Testing | Completed | 5 | Day 8: 5
US-M4-SEC | N9 | Reviewed role restrictions across application and disbursement APIs. | 04-08-2026 | 04-08-2026 | Niharika | Security Review | Completed | 5 | Day 9: 5
US-M4-SEC | N10 | Validated unauthorized-access handling and identified security issues for correction. | 05-08-2026 | 05-08-2026 | Niharika | Security Testing | Completed | 4 | Day 10: 4
US-M4-API | K1 | Review existing REST endpoints and map them to the correct role restrictions. |  |  | Kishore Kumar | API Security | Completed | 6 | Day 1: 6
US-M4-API | K2 | Add method-level authorization to beneficiary, scheme and disbursement APIs. |  |  | Kishore Kumar | API Security | Completed | 7 | Day 2: 7
US-M4-API | K3 | Implement treasury release-funds integration endpoint. |  |  | Kishore Kumar | Treasury Integration | Completed | 7 | Day 3: 7
US-M4-API | K4 | Implement beneficiary database verification endpoint with error handling. |  |  | Kishore Kumar | Beneficiary Integration | Completed | 6 | Day 4: 6
US-M4-API | K5 | Document secured endpoints and prepare Postman role-based test collection. |  |  | Kishore Kumar | API Documentation | Completed | 5 | Day 5: 5
US-M4-AUD | R1 | Review audit requirements and identify compliance-relevant actions requiring logs. |  |  | Ravi Teja | Audit Design | Completed | 4 | Day 1: 4
US-M4-AUD | R2 | Design audit-log data structure with actor, role, action, entity, timestamp and values. |  |  | Ravi Teja | Database Design | Completed | 5 | Day 2: 5
US-M4-AUD | R3 | Prepare AuditLog entity/model. |  |  | Ravi Teja | Backend Development | Completed | 5 | Day 3: 5
US-M4-AUD | R4 | Create audit-log repository using JPA. |  |  | Ravi Teja | Backend Development | Completed | 4 | Day 4: 4
US-M4-AUD | R5 | Design reusable audit logging service. |  |  | Ravi Teja | Service Design | Completed | 5 | Day 5: 5
US-M4-AUD | R6 | Connect audit logging to verification actions. |  |  | Ravi Teja | Audit Integration | Completed | 6 | Day 6: 6
US-M4-AUD | R7 | Connect audit logging to approval/rejection actions. |  |  | Ravi Teja | Audit Integration | Completed | 6 | Day 7: 6
US-M4-AUD | R8 | Connect audit logging to finance/disbursement actions. |  |  | Ravi Teja | Audit Integration | Completed | 6 | Day 8: 6
US-M4-AUD | R9 | Prepare audit-log retrieval API with ADMIN and DISTRICT_OFFICER restrictions. |  |  | Ravi Teja | Audit API | Completed | 4 | Day 9: 4
US-M4-AUD | R10 | Test audit entries for approval, rejection and disbursement scenarios. |  |  | Ravi Teja | Audit Testing | Completed | 5 | Day 10: 5
US-M4-FE | S1 | Review frontend authentication requirements and plan login flow. |  |  | SreeLakshmi | Frontend Planning | Completed | 4 | Day 1: 4
US-M4-FE | S2 | Design login page structure and validation requirements. |  |  | SreeLakshmi | Frontend Development | Completed | 5 | Day 2: 5
US-M4-FE | S3 | Implement login UI and input validation. |  |  | SreeLakshmi | Frontend Development | Completed | 6 | Day 3: 6
US-M4-FE | S4 | Connect frontend login flow with authentication API. |  |  | SreeLakshmi | Authentication Integration | Completed | 6 | Day 4: 6
US-M4-FE | S5 | Implement authentication state/token handling. |  |  | SreeLakshmi | Authentication Integration | Completed | 5 | Day 5: 5
US-M4-FE | S6 | Implement protected routes for authenticated pages. |  |  | SreeLakshmi | Route Protection | Completed | 6 | Day 6: 6
US-M4-FE | S7 | Implement role-based route restrictions. |  |  | SreeLakshmi | Frontend RBAC | Completed | 6 | Day 7: 6
US-M4-FE | S8 | Update sidebar/navigation visibility based on user role. |  |  | SreeLakshmi | Frontend RBAC | Completed | 5 | Day 8: 5
US-M4-FE | S9 | Add logout handling and authentication-state cleanup. |  |  | SreeLakshmi | Authentication | Completed | 4 | Day 9: 4
US-M4-FE | S10 | Handle invalid/expired authentication and redirect to login. |  |  | SreeLakshmi | Authentication QA | Completed | 5 | Day 10: 5
US-M4-QA | A1 | Prepare production-like application configuration and database environment setup. |  |  | Akshara | Deployment Preparation | Completed | 5 | Day 1: 5
US-M4-QA | A2 | Prepare Maven build/run instructions and fresh database setup script. |  |  | Akshara | Deployment Preparation | Completed | 5 | Day 2: 5
US-M4-QA | A3 | Prepare system architecture and installation/setup documentation. |  |  | Akshara | Documentation | Completed | 6 | Day 3: 6
US-M4-QA | A4 | Compile API documentation and role/permission summary. |  |  | Akshara | Documentation | Completed | 5 | Day 4: 5
US-M4-QA | A5 | Run end-to-end QA across registration, eligibility, verification, disbursement and analytics. |  |  | Akshara | QA Testing | Completed | 8 | Day 5: 8
US-M4-QA | A6 | Log integration defects and verify fixes across modules. |  |  | Akshara | Bug Tracking | Completed | 6 | Day 6: 6
US-M4-QA | A7 | Prepare screenshots, test evidence and final project report. |  |  | Akshara | Final Documentation | Completed | 6 | Day 7: 6
TOTAL ESTIMATED HOURS

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Milestone 1 | Day 1 | No major impediment | Kishore set up the development environment; Ravi began database design; Akshara defined API standards; SreeLakshmi started workflow design; Niharika coordinated the foundation work.
Milestone 1 | Day 2 | No major impediment | Database/ER design, API list and workflow diagrams progressed.
Milestone 2 | Day 1 | No major impediment | Kishore worked on Beneficiary/Scheme APIs; Ravi worked on eligibility/database; Akshara worked on Application module; SreeLakshmi worked on verification workflow; Niharika coordinated authentication/integration.
Milestone 2 | Day 2 | No major impediment | Core backend modules and workflow implementation progressed.
Milestone 2 | Day 3 | Application/database integration required checking | Application and eligibility modules were connected and tested.
Milestone 2 | Day 4 | No major impediment | Verification routing, authentication and REST API testing progressed.
Milestone 2 | Day 5 | No major impediment | Integration issues were reviewed and API/workflow behavior was tested.
Milestone 2 | Day 6 | No major impediment | End-to-end module testing and milestone preparation progressed.
Milestone 3 | Day 1 | No major impediment | Niharika designed disbursement/milestone schema; Kishore prepared disbursement API structure; Ravi created compliance milestone structure; SreeLakshmi wireframed dashboard; Akshara designed analytics query layer.
Milestone 3 | Day 2 | No major impediment | Core scheduling, controller APIs, due-date logic, dashboard components and analytics REST APIs were implemented.
Milestone 3 | Day 3 | No major impediment | Fund-release trigger, actual-vs-scheduled tracking, non-compliance flags, live dashboard integration and budget/category analytics progressed.
Milestone 3 | Day 4 | No major impediment | Integration testing, disbursement API testing, reminder automation, analytics charts and PDF/Excel export work progressed.
Milestone 3 | Day 5 | Frontend/API integration issues | API bugs were fixed, compliance flow tested, dashboard polished, exports completed and documentation drafted.
Milestone 3 | Day 6 | No major impediment | Final system test, API/demo collection, compliance walkthrough, dashboard demo flow and documentation verification were completed.
Milestone 4 | 23-07-2026 | No major impediment | Niharika reviewed security architecture and role hierarchy; team members began security, audit, frontend-authentication and deployment/QA preparation.
Milestone 4 | 24-07-2026 | No major impediment | Role permissions, audit fields, login UI and supporting API/security documentation were progressed.
Milestone 4 | 27-07-2026 | No major impediment | Authentication flow, protected endpoints, AuditLog structure, login implementation and final API documentation progressed.
Milestone 4 | 28-07-2026 | No major impediment | Security configuration, treasury integration design, audit repository, login integration and Application module validation progressed.
Milestone 4 | 29-07-2026 | No major impediment | Password hashing, treasury endpoint, audit service, frontend authentication state and Application repository work progressed.
Milestone 4 | 30-07-2026 | No major impediment | Endpoint authorization, beneficiary integration, audit logging and protected frontend routes progressed.
Milestone 4 | 31-07-2026 | No major impediment | Security review, integration error handling, audit approval logging, frontend role restrictions and Application API completion progressed.
Milestone 4 | 03-08-2026 | No major impediment | Authentication scenarios, Postman integration tests, disbursement audit logging, role-based sidebar and MySQL configuration were reviewed.
Milestone 4 | 04-08-2026 | No major impediment | Application/disbursement role restrictions, API authorization, audit retrieval, logout and Spring Boot API behavior were reviewed.
Milestone 4 | 05-08-2026 | No major impediment | Unauthorized-access handling, integration documentation, audit testing, expired-authentication handling and Application API test scenarios were progressed.
Milestone 4 | 06-08-2026 | Git/file state required checking for Akshara | Security changes, integration error cases, audit consistency, four-role navigation and required project files were reviewed/restored.
Milestone 4 | 07-08-2026 | No major impediment | Role access, API documentation, audit endpoint restrictions, secured frontend integration and project documentation were reviewed.
Milestone 4 | 10-08-2026 | No major impediment | Security documentation, endpoint authorization, audit documentation, frontend screens and final deployment/documentation planning progressed.
Milestone 4 | 11-08-2026 | No major impediment | Final RBAC validation, API test evidence, audit test scenarios, frontend access-control tests and final documentation/setup-guide structure were prepared.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | All Milestones |  |  | Niharika | Start documenting role decisions and integration risks from the beginning. | Stop waiting until final integration to identify security/access mismatches. | Continue coordinating reviews and validating cross-module behavior. | Keep RBAC, security and integration decisions synchronized across the team.
2 | All Milestones |  |  | Kishore Kumar | Start testing secured endpoints with role-specific tokens earlier. | Stop postponing integration testing until all modules are merged. | Continue maintaining API/Postman documentation with endpoint changes. | Use incremental API testing and document security requirements alongside development.
3 | All Milestones |  |  | Ravi Teja | Start validating audit/compliance behavior against real workflow actions earlier. | Stop treating audit and compliance logic as isolated database work. | Continue checking data consistency and testing eligibility/compliance logic. | Coordinate audit, eligibility and compliance validation with workflow changes.
4 | All Milestones |  |  | SreeLakshmi | Start frontend/backend integration checks earlier. | Stop relying on mock data until late integration. | Continue testing role-based navigation and dashboard behavior. | Keep frontend route/sidebar permissions aligned with backend RBAC.
5 | All Milestones |  |  | Akshara | Start integration verification and documentation updates earlier. | Stop waiting until the end to verify database/configuration dependencies and exports. | Continue API documentation, QA, reporting and deployment preparation. | Maintain synchronized documentation and perform end-to-end checks while modules evolve.